# Bankability Document Checklist

Thar Sun 100 MWp | SunAxis single-axis tracker | Status as of 24-Oct-2026

FICTIONAL deal. Use as a template: the document list reflects what lenders and independent engineers typically ask of a tracker supplier.

| # | Document | What the lender / IE checks | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | Audited financial statements (3 years) | Supplier can honour warranties and LDs over the project life | SunAxis Finance | Available |
| 2 | Track record and reference list | MW installed and operating years by region; similar climate (desert, dust, high wind) | SunAxis Sales | Available |
| 3 | IEC 62817 design-qualification certificate | Tracker design tested to the international tracker standard | SunAxis Engineering | Available |
| 4 | Structural calculations and wind-tunnel study | Static/dynamic wind loads, stow angle, IS 875 (Part 3) design wind speed | SunAxis Engineering | Site-specific: in preparation |
| 5 | Independent engineer (IE) technical due-diligence report | Third-party review of design, quality and field performance | IE (customer's lender) | To request |
| 6 | Energy yield assessment (P50 / P90) | Bankable yield with real layout, GCR, backtracking. PVGIS is screening only | Customer's yield consultant | To request |
| 7 | Warranty terms and warranty backing | Coverage periods, exclusions, parent guarantee or insurance behind the warranty | SunAxis Legal | Draft |
| 8 | Quality plan, ITP and factory audit report | Inspection & test plan, sampling, welding and galvanising controls | SunAxis Quality | Available |
| 9 | Corrosion protection specification | Hot-dip galvanising (ISO 1461) thickness vs site corrosivity class | SunAxis Engineering | Available |
| 10 | Pile design and pile load-test plan | Based on site geotechnical report; pull-out and lateral load tests | SunAxis + Customer EPC | Pending geotech report |
| 11 | Control system, stow strategy and cybersecurity note | Wind/hail stow logic, communications redundancy, SCADA integration, cyber controls | SunAxis Controls | Available |
| 12 | Supply agreement: LDs, performance security, insurance | Delay/performance LDs, bank guarantees, insurance certificates | SunAxis Legal / Finance | Draft |
| 13 | Delivery schedule and logistics plan | Credible plan to meet COD; port/road route; site storage | SunAxis Logistics | In preparation |
| 14 | O&M manual, spare parts list, availability guarantee | Tracker availability (e.g. ≥99%) and spares strategy | SunAxis Service | Available |

## Analyst actions before quote submission (06-Nov-2026)

- Send items 1, 2, 3, 8, 9, 11 and 14 with the quotation as the bankability binder (index + PDFs).

- Ask the customer for the geotechnical report and their lender's IE contact, which unblocks items 4, 5 and 10.

- Offer an independent energy-yield review (item 6) to support the yield argument in the quotation.

- Track each item in Salesforce as a task on the Thar Sun opportunity, with an owner and a due date.